## Slide 1: EVS-3 Program August 22, 2023
Melissa Martin (EVS-3 MM)
Barry Lefer (EVS-3 PS)
Deborah Smith (Airborne Data Management Group - ADMG)
Earth System Science Pathfinder Program

## Slide 2: Topics for Discussion
Lessons learned
Open data workshops
Inclusivity, inclusion, and diversity
Optimized post-flight data analysis and dissemination
Strategies used for using final dollars such as those in reserves
How to keep the Investigation science going after completion of EVS Investigation
Types of overview papers that have been done
Opportunities for collaboration across the EVS Investigations? Mission synergies to be taken advantage of?
Final data archive, synchronized data, data release date

## Slide 3: Inclusivity
Investigation Code of Conducts / Agreements of behavior
  Required Investigation documentation
  To be developed as a team for overall buy-in
Accessibility: Shared drive accessible to all participants (NASA and non-NASA)
Communications within the science team
  Frequency of meetings, openness, communication platform used, etc.
  Inner-project deployment communication (lines of authority)
  Recommend 1:1 point of contact between science and aircraft ops for decisions, flight schedules, engineering, modifications, requirements, etc. to ensure both orgs know where decisions are coming from and how to disseminate to respective orgs.
  Open communication: When a request or activity cannot be executed/approved, it is helpful for the teams to understand the rationale

## Slide 4: Planning
SOFRS (Science Operations Flight Request System):
  to be kept up to date and to include all pertinent information including all PIs and funding Program Managers
Deployment site visits/survey:
  critical to the success of the campaign and needs to be done in advance.
  should include alternative locations (diverts, moving operations, etc.)
Schedules and operational windows:
  Should be clearly defined during the planning phase
  Contingency plans should be established which incorporate flexibility in the schedule
  Important to recognize risks to schedules and deployment locations, such as aircraft availability, ship availability, personnel availability, weather, etc.
  Need back-up flight scientists and operators for instruments
Budgetary considerations:
  Any changes (even minor changes) from budgeted aircraft ops plan can result in increases higher than expected. Need as many details as possible laid out in advance to understand costs (e.g. pace of operations, weekend flights, suitcase flts, double sorties).
Personnel:
  Roles and responsibilities should be clearly defined
  Commitments from Investigation science teams need to be established before the start of the campaign to prevent interruptions in the field support
Emergency management, guidelines, reporting and procedures should be developed and clearly understood (at least by the Investigation management team)
Flight planning:
  It is beneficial to have a pilot on the ground to help with flight planning (while a flight is going on) especially if the flight being planned is complicated. This might be at an additional cost.

## Slide 5: Data Management
Requirements at ICR:
  Data quality analysis is needed at the individual PI level and project level to provide a wholistic picture and ensure project data quality.
  At least two data submission deadlines may be needed, one for individual co-Is and the second one for an independent assessment of all data to check for consistency especially between the closely related measurements.
  Sampling time synchronization requirements
At project start, Project Scientist should meet with each instrument co-I individually to:
  Reaffirm measurements or products that are required for the archive and separate any additional value added products (beyond level 1 science requirements) that will not tracked by the Investigation or Program office.
  Determine if there are any dependencies on other datasets and how each team would deal with delays from those dependencies.
  Determine how data is going to be time stamped relative to other measurements and get agreements that the team will address any issues determined from the data archive.
  Get commitment to meet archive schedule from each instrument Co-I.
  After meeting instrument Co-Is individually, meet as a group to discuss overall schedule.
  Issues with meeting schedule should be resolved before data collection begins (include ESSP/HQ)
  Establish process with ESSP/HQ for re-evaluating data deadlines in case of unexpected contingencies, schedule changes, or new commitments.
Prior to each deployment:
  Meet with each instrument co-I to review required data products and schedule. Discuss any new commitments/projects that may impact ability to meet schedule.
  Discuss issues with ESSP/HQ to resolve
  Decide on policy for status checks
Post deployment
  Perform status checks and plan for evaluating the datasets for consistency (e.g. time sync, reporting intervals).
  Identify issues with meeting deadlines at earliest possible time
  Engage ESSP/HQ if needed to adjust timeline and relate potential long-term impacts
For late data:
  Archive any data without dependencies on schedule but Project Scientist should get agreements to that an update will be provided once dependencies are available.
  Make archive schedule and status check schedule
Once archive is complete, perform integrated analysis to cross check data agreement/alignment

## Slide 6: Open Data Workshop
What is NASA looking for here?
Lessons learned from Open Data Workshops
ESSP PO applications funded: Delta-X applications workshop
Improve airborne and field data stewardship